| Date | 1 October 2026 |
| --- | --- |
| Team ID | PER206 AI WeatherWise API |
| Project Name | AI WeatherWise API |
| Maximum Marks | 5 Marks |

# Product Backlog, Sprint Schedule, and Estimation (4 Marks)

Proposed schedule: three one-week sprints. Story points estimate relative effort; dates and team allocations are proposed for planning.

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members | Sprint Start Date | Sprint End Date (Planned) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Setup | USN-1 | As a developer, I can configure the API and connect to MongoDB using environment settings. | 2 | High | BHAVYA M A | 01 Oct 2026 | 07 Oct 2026 |
| Sprint-1 | Registration | USN-2 | As a user, I can register with my name, email, and password; my password is stored as a hash. | 3 | High | BRAGGATHISHWARI B | 01 Oct 2026 | 07 Oct 2026 |
| Sprint-1 | Login | USN-3 | As a user, I can log in with email and password to receive a JWT. | 2 | High | BHAVANA S S | 01 Oct 2026 | 07 Oct 2026 |
| Sprint-1 | Authentication | USN-4 | As a user, I can access my profile with a valid Bearer token; invalid tokens are rejected. | 2 | High | BAVATHARANI R | 01 Oct 2026 | 07 Oct 2026 |
| Sprint-2 | Favorite creation | USN-5 | As an authenticated user, I can save a favorite city and country linked to my account. | 3 | High | BHAVYA M A | 08 Oct 2026 | 14 Oct 2026 |
| Sprint-2 | Favorite retrieval | USN-6 | As an authenticated user, I can retrieve my saved favorite locations. | 2 | High | BHAVANA S S | 08 Oct 2026 | 14 Oct 2026 |

| Date | 1 October 2026 |
| --- | --- |
| Team ID | PER206 AI WeatherWise API |
| Project Name | AI WeatherWise API |
| Maximum Marks | 5 Marks |

# Product Backlog, Sprint Schedule, and Estimation (4 Marks)

Proposed schedule: three one-week sprints. Story points estimate relative effort; dates and team allocations are proposed for planning.

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members | Sprint Start Date | Sprint End Date (Planned) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sprint-2 | Favorite management | USN-7 | As a user, I can update or delete my favorite locations; other users cannot modify them. | 3 | High | BAVATHARANI R | 08 Oct 2026 | 14 Oct 2026 |
| Sprint-2 | Validation and errors | USN-8 | As an API user, I receive clear errors for duplicate favorites, missing fields, invalid tokens, and denied actions. | 2 | High | BRAGGATHISHWARI B | 08 Oct 2026 | 14 Oct 2026 |
| Sprint-3 | Weather retrieval | USN-9 | As a user, I can request current city weather from OpenWeatherMap or receive clearly marked mock fallback data. | 5 | High | BHAVYA M A | 15 Oct 2026 | 21 Oct 2026 |
| Sprint-3 | AI recommendations | USN-10 | As an authenticated user, I can supply temperature and conditions to receive Gemini advice or local rule-based advice. | 2 | Medium | BHAVANA S S | 15 Oct 2026 | 21 Oct 2026 |
| Sprint-3 | Weather summary | USN-11 | As an authenticated user, I can supply city weather values and receive a concise Gemini summary or local fallback. | 3 | High | BAVATHARANI R | 15 Oct 2026 | 21 Oct 2026 |
| Sprint-3 | Verification and documentation | USN-12 | As a developer, I can verify authentication, favorites, weather, AI, and fallback cases using Postman and document the demonstration. | 3 | High | BHAVYA M A | 15 Oct 2026 | 21 Oct 2026 |

Sprint estimates: Sprint-1 = 9 points; Sprint-2 = 10 points; Sprint-3 = 13 points. Total = 32 points.